## Sheet1
Running an IIBA Member Event - Checklist Refer to Word Document for Supporting Notes
Event name:
Event date:
Time:
What | Who | Comments
One month before:
Identify the preferred date (and alternatives)
Confirm volunteers and responsibilities |  | Who has the banner?
Ensure speaker is confirmed |  | Need to get speakers for year ahead then just confirm.
Book the venue and check access/security requirements and parking availability
Post the event on Meetup
Post the event on Twitter and LinkedIn
Assign responsibility for responding to Meetup comments
Manage RSVP's |  | Only for closed events.
The week before
Check the speaker's requirements - technical, whiteboard, stationery, etc - and if they will share notes
Confirm date, timing and security with venue
Confirm which committee members and volunteers are attending - allocate final tasks
Order catering
Purchase thank you gift for the speaker + gift bag
Two days before
Send reminder to attendees re location and timing and contact details (Note that Meetup does this automatically one day before an event.)
Extract RSVP list from Meetup
Provide list of attendees to venue (if required)
Confirm who will setup IIBA banner
The day before
Track late RSVP changes, add to list
Print out name tags
Confirm Catering and drinks (if required)
On the day
Finalise attendee list
Set table out for name tags
Display IIBA banner
Set up chairs and tables
Check that required equipment is working correctly
Welcome speaker and help them get set up, put out water for them
Welcome participants - give them name tags - direct to refreshments - maintain attendance list
Have someone on hand to take last minute queries and to make newcomers feel welcome
5 Mins before start
Guide participants to take seats
At beginning of proceedings
Welcome everyone and make mention of newcomers
Housekeeping notices - exits, bathrooms, phones off or on silent
Thanks to provider of venue
Thanks to IIBA sponsors
Introduce speaker and outline format, Q&A, etc.
Once speaker has completed presentation
Facilitate Q&A
Thank speaker and present gift
Thank host for venue
Thank IIBA sponsors
Thank attendees
Notify all of next event
Ask for suggestions, volunteers and speaker suggestions
Take stock of refreshments inventory
Clean up venue
Ensure IIBA banner is stored or taken home
Secure / lock-up venue
The day after
Write a final thank you to attendees on Meetup and post speaker handout if available
Write to speaker to thank them and post on Twitter/Linked In
Arrange the next committee meeting
Complete IIBA form and submit attendance list to IIBA for PDU/CDU points |  | Only for closed events.